BLACKBAR

PHASED IMPLEMENTATION ROADMAP

From Corpus to Courtroom: A Four-Phase Build Plan

| Version: | 2.0 |
| --- | --- |
| Date: | March 13, 2026 |
| Total Duration: | 16–20 weeks |
| First Output: | Week 6 (slip-and-fall POC) |

# Implementation Overview

The roadmap sequences BlackBar's build around one principle: get Lane producing real drafts on real cases as fast as possible, then expand scope. Phase 1 targets slip-and-fall premises liability — the highest-volume, most templated case type with the deepest precedent corpus. Each subsequent phase adds a case type domain and an agent capability.

## Phase Summary

| Phase | Duration | Scope | Key Milestone |
| --- | --- | --- | --- |
| 1. Foundation | Weeks 1–6 | Corpus ingestion + Agent 1 (Intake) + Agent 4 (Draft Assembly) for slip-and-fall only | First AI-assisted slip-and-fall draft on a live case |
| 2. Intelligence | Weeks 7–10 | Agent 2 (Standards) + Agent 3 (Precedent/Adversarial) + opposing expert corpus | Automated standards matrix + opposing expert dossier generation |
| 3. Hardening | Weeks 11–14 | Agent 5 (QC) + Daubert compliance layer + full premises liability coverage | End-to-end pipeline producing QC-validated reports across all PL sub-types |
| 4. Expansion | Weeks 15–20 | Design & Construction cases + Clio integration + rebuttal workflow + production hardening | Full BlackBar deployment across all SCG practice areas |

# Phase 1: Foundation (Weeks 1–6)

Objective: Get Lane producing a real slip-and-fall draft on a live case using AI assistance by Week 6.

## Week 1–2: Corpus Ingestion

| Task | Owner | Deliverable |
| --- | --- | --- |
| Parse all 704 Premises Liability PDFs using Docling/Unstructured.io | Dev team | Structured text corpus with metadata |
| Chunk documents with metadata schema (case type, sub-type, jurisdiction, venue, report type, section type, codes cited) | Dev team | Vector store populated with PL corpus |
| Extract Lane's report templates: identify section structures, heading patterns, citation formats, reasoning flows across 50+ reports | Dev team + Lane (2 hrs review) | Template library with structural patterns |
| Voice analysis: extract characteristic language patterns, sentence structures, terminology preferences from corpus | Dev team | Voice calibration profile |
| Build structured intake form (web or mobile) for site photos, notes, consultant blurb | Dev team | Intake form deployed |

## Week 3–4: Agent 1 (Intake & Classification)

| Task | Owner | Deliverable |
| --- | --- | --- |
| Build Agent 1: case type classification from photos + notes + blurb | Dev team | Agent 1 deployed |
| Implement jurisdiction resolver (address → Clark County/Henderson/LV/NLV/Reno/Boulder City) | Dev team | Jurisdiction mapping service |
| Implement Claude Vision integration for site photo processing (EXIF, scene description, condition documentation) | Dev team | Photo processing pipeline |
| Test Agent 1 against 20 historical cases (known classifications). Target: 95%+ accuracy. | Dev team + Lane (1 hr review) | Validation report |

## Week 5–6: Agent 4 (Draft Assembly) — Slip-and-Fall Only

| Task | Owner | Deliverable |
| --- | --- | --- |
| Build Agent 4 with slip-and-fall template: Observation → Standard → Analysis → Opinion structure | Dev team | Agent 4 (slip-and-fall scope) |
| Implement voice calibration from corpus analysis. Integrate precedent retrieval (simple similarity search, no full Agent 3 yet). | Dev team | Voice-calibrated draft engine |
| Implement .docx output with Lane's formatting: headers, numbering, exhibit references, photo embedding, DRAFT watermarks | Dev team | Court-formatted .docx generation |
| Run Agent 4 against 5 historical slip-and-fall cases. Lane reviews outputs for voice fidelity and structural accuracy. | Lane (3 hrs review) | Phase 1 validation: Lane approval |
| ★ MILESTONE: First AI-assisted draft on a live slip-and-fall case | Lane | Production use begins |

# Phase 2: Intelligence (Weeks 7–10)

Objective: Add standards resolution and adversarial intelligence. Transform BlackBar from a drafting tool into a forensic reasoning engine.

## Week 7–8: Agent 2 (Standards & Code Resolution)

| Task | Owner | Deliverable |
| --- | --- | --- |
| Build PostgreSQL standards database: ingest ICC, ASTM, ANSI, NFPA, IES, NFSI standards with section-level granularity | Dev team | Standards DB populated |
| Map jurisdiction → adopted code editions for Clark County, Henderson, Las Vegas, NLV, Reno, Boulder City | Dev team + Lane (1 hr) | Jurisdiction-edition mapping |
| Ingest Nevada development codes: Title 30, Henderson Dev Code, LV UDC, NLV Dev Code, Reno Dev Code, Boulder City | Dev team | Development codes in DB |
| Build Agent 2: classification + jurisdiction → applicable standards matrix with specific section references | Dev team | Agent 2 deployed |
| Validate against 10 historical cases: compare Agent 2's standards matrix to Lane's actual citations | Lane (1 hr review) | Standards accuracy validation |

## Week 9–10: Agent 3 (Precedent & Adversarial Retrieval)

| Task | Owner | Deliverable |
| --- | --- | --- |
| Ingest all 224 opposing expert reports with metadata: expert name, firm, case type, methodology, key positions | Dev team | Opposing expert corpus in vector store |
| Build opposing expert profiles: reasoning patterns, methodology gaps, prior contradictions, cross-examination vulnerabilities for each of the 11 named experts | Dev team + Lane (2 hrs) | 11 adversarial intelligence profiles |
| Build Agent 3 Path A: SCG corpus retrieval with same-client, same-expert priority weighting | Dev team | Precedent retrieval engine |
| Build Agent 3 Path B: opposing expert dossier generation from adversarial library | Dev team | Adversarial intelligence engine |
| Integrate Gate 1 workflow: Lane reviews intake card + standards matrix + precedent set before draft assembly | Dev team | Human-in-the-loop Gate 1 |
| ★ MILESTONE: Automated standards matrix + opposing expert dossier on demand |  | Intelligence layer operational |

# Phase 3: Hardening (Weeks 11–14)

Objective: Add QC/cross-examination hardening, Daubert compliance layer, and expand to full premises liability coverage.

## Week 11–12: Agent 5 (QC & Cross-Examination Hardening)

| Task | Owner | Deliverable |
| --- | --- | --- |
| Build citation verification engine: every code reference resolves to a real, current section in standards DB | Dev team | Citation verifier |
| Build logic audit: opinion-to-fact traceability check, unsupported conclusion detection | Dev team | Logic auditor |
| Build consistency checker: compare current opinions against Lane's positions in prior cases on same issues | Dev team | Position consistency engine |
| Implement DRAFT watermarking and tracked-change audit trail for Daubert defensibility | Dev team | Daubert compliance layer |
| Integrate Gate 2 workflow: Lane reviews annotated draft with QC flags | Dev team | Human-in-the-loop Gate 2 |

## Week 13–14: Full Premises Liability Expansion

| Task | Owner | Deliverable |
| --- | --- | --- |
| Extend Agent 4 templates to all PL sub-types: trip/fall, stairway, lighting, ADA, bathing/swimming, landscape, fire, FFE | Dev team + Lane (3 hrs) | Full PL template library |
| End-to-end pipeline testing: run 3 live cases through full 5-agent pipeline with both gates | Lane (4 hrs total) | Pipeline validation on live cases |
| Legal review: Lane's litigation attorney validates Daubert positioning, audit trail, and deposition strategy | Lane's attorney | Legal clearance memo |
| ★ MILESTONE: Full end-to-end pipeline across all Premises Liability sub-types |  | PL pipeline production-ready |

# Phase 4: Expansion (Weeks 15–20)

Objective: Expand to Design & Construction cases, add rebuttal workflow, integrate Clio case management, and harden for full production.

## Week 15–16: Design & Construction Domain

| Task | Owner | Deliverable |
| --- | --- | --- |
| Ingest 168 Design & Construction PDFs: contracts, OSHA, estimating, codes, pools, residential, public works | Dev team | D&C corpus in vector store |
| Extract D&C-specific templates and extend Agent 4 for contract claims, construction defects, OSHA compliance, jobsite safety | Dev team + Lane (2 hrs) | D&C template library |
| Extend standards DB with OSHA regulations, contract law references, estimating standards | Dev team | Expanded standards DB |

## Week 17–18: Rebuttal Workflow & Clio Integration

| Task | Owner | Deliverable |
| --- | --- | --- |
| Build rebuttal-specific Agent 4 variant: point-by-point opposing report analysis with cross-reference to expert dossier contradictions | Dev team | Rebuttal draft engine |
| Integrate Clio API: conflict checks, deadline tracking, case number assignment, billing time capture | Dev team + Lane (1 hr config) | Clio integration live |
| Build Photo/Video Analysis workflow: extend Agent 1 classification for surveillance and aerial imagery cases | Dev team | Photo/video case type support |

## Week 19–20: Production Hardening

| Task | Owner | Deliverable |
| --- | --- | --- |
| Implement OAuth 2.0 + RBAC: Lane-only access for opinion adoption; staff access for intake | Dev team | Authentication layer |
| Set up S3/Azure Blob storage with versioning for case files, photos, and generated reports | Dev team | File storage infrastructure |
| Implement monitoring, logging, and error handling across all 5 agents | Dev team | Observability layer |
| Full system testing: 5 live cases across PL, D&C, and Photo/Video with full pipeline | Lane (5 hrs total) | Full system validation |
| ★ MILESTONE: Full BlackBar deployment across all SCG practice areas |  | BlackBar v2.0 production launch |

# Resource Requirements

## Lane's Time Commitment

| Phase | Hours | Activities |
| --- | --- | --- |
| Phase 1: Foundation | 6 hrs | Template review (2 hrs), classification validation (1 hr), draft review (3 hrs) |
| Phase 2: Intelligence | 4 hrs | Standards validation (1 hr), adversarial profile review (2 hrs), Gate 1 testing (1 hr) |
| Phase 3: Hardening | 7 hrs | Template expansion (3 hrs), live case testing (4 hrs) |
| Phase 4: Expansion | 8 hrs | D&C templates (2 hrs), Clio config (1 hr), full system testing (5 hrs) |
| TOTAL | ~25 hrs | Spread across 20 weeks (~1.25 hrs/week average) |

## Development Team Estimate

Assumes a 2-person team (1 ML/AI engineer + 1 full-stack engineer) working full-time:

| Component | LOE | Complexity Driver |
| --- | --- | --- |
| Corpus ingestion + vector store | 3–4 weeks | 1,109 PDFs, metadata extraction, chunking strategy |
| Agent 1 (Intake/Classification) | 2 weeks | Vision integration, jurisdiction resolver, conflict check |
| Agent 2 (Standards/Codes) | 2–3 weeks | Standards DB build, jurisdiction-edition mapping |
| Agent 3 (Precedent/Adversarial) | 2–3 weeks | Dual retrieval paths, adversarial profiling |
| Agent 4 (Draft Assembly) | 3–4 weeks | Voice calibration, template engine, .docx generation |
| Agent 5 (QC/Hardening) | 2–3 weeks | Citation verification, logic audit, consistency check |
| Infrastructure (auth, storage, Clio) | 2–3 weeks | OAuth, S3, API integration, monitoring |
| Integration testing + production hardening | 2–3 weeks | End-to-end pipeline validation on live cases |

# Risk Register

| Risk | Severity | Impact | Mitigation |
| --- | --- | --- | --- |
| Daubert challenge to AI-assisted reports | HIGH | Expert opinions ruled inadmissible if court determines AI, not expert, generated the conclusions | Draft watermarking, tracked-change audit trail, deposition positioning strategy. Legal review in Phase 3. |
| Voice drift from Lane's established patterns | HIGH | Stylistic inconsistency exploitable on cross-examination as evidence expert did not author the report | Corpus-trained voice calibration. Lane reviews every draft. Consistency checker in Agent 5. |
| Hallucinated code citations | HIGH | Citing nonexistent code sections destroys expert credibility | Standards DB as ground truth. Agent 5 verifies every citation resolves to real, current section. |
| Jurisdiction-edition mismatch | MEDIUM | Citing wrong code edition for jurisdiction undermines analysis | Structured jurisdiction-to-edition mapping in standards DB. Agent 2 resolves before draft. |
| Opposing expert corpus staleness | LOW | Adversarial profiles outdated as experts evolve their methodology | Incremental ingestion pipeline. New opposing reports added as cases close. |
| Lane adoption friction | MEDIUM | Expert rejects AI drafts as too different from his natural output, abandons tool | Phase 1 POC on highest-volume case type. Iterative voice calibration with Lane's direct feedback. |

END OF IMPLEMENTATION ROADMAP